Iteration 4 Plan
Team Anonymous
Student Number	Team Member Name
7538073	Alexander Covlin
8311382	Michael Munchin
7377495	Luke Durkan
7627505	Darran Kartaschew

Tutor: Renford Law
Version: 1.1
Date: 10/10/2012

# Iteration 4 Plan Summary
## Release 2 – iteration 2.
Delivery date: 24-Oct-2012	Total Story Points:23
Current Velocity: 20

Model Refinement and Mobile Application
The system will be accessible from the Android mobile platform so users will be able to access this product through a portable system, which will allow for location fetching through GPS, and utilisation of mobile sensors now common on most smart phones.
This feature will also include the ability to print reports on the desktop version of the system, for customers who want to take system details with them.
Story ID	Story Title	Story Points
22	Mobile Application (Part B)	4
23	Saving Reports	4
24	Printing Reports	1
26	Location Fetching (Mobile)	2
28	Compare two configurations	8
32	Efficiency Checking	2
33	Display Panel Output Details	2
	Story Point Sub-Total:	23

# Iteration Plan
Total Points:	23	Total Hours: 78
### Story 22: Mobile Application (part B)
Note: The aim of Part B is to modify the application to take advantage of mobile form factor, and touch input of the device.
Also to take advantage of any onboard sensors to assist the user in input of information.
Task ID	Task Description	Estimate	Taken
1	Enable Swipe navigation of wizard	2	1
2	Create Unit test for Swipe action for navigation	4	1
3	Enable use of onboard GPS to determine location	4	1
4	Enable use of onboard gyro's to determine angles for panel setup	4	2
	Story Points: 4 Total Hours:	14	5

### Story 23: Saving Reports
Note: The aim of this task is to save reports to the local device only, not GAE or other cloud storage. (Store complete results data for displaying in application, not just textual report).
Task ID	Task Description	Estimate	Taken
1	Create menu to save current configuration/report (desktop)	1
2	Create button to save report to local device	1	1
3	Create menu to retrieve report from local device	1	1
4	Create functions to store and retrieve solar setup and solar results from local storage (desktop)	2
5	Create functions to store and retrieve solar setup and solar results from local storage (mobile)	4	3
6	Modify UI to handle retrieval of reports and move directly to results pane. (desktop)	2
7	Modify UI to handle retrieval of reports and move directly to results pane. (mobile)	2	4
8	Create Unit tests for storing and retrieving results files.	3
	Story Points: 4 Total Hours:	14	9

### Story 24: Printing Reports
Note: This feature is for the desktop application only.
Task ID	Task Description	Estimate	Taken
1	Create menu option for printing, including printer setup	2
2	Create button for printing in results pane in wizard	1
3	Create print output suitable for printing	1
	Story Points: 1 Total Hours:	4	0

### Story 26: Location Fetching (Mobile)
Note: This feature is for the mobile application only.
Task ID	Task Description	Estimate	Taken
1	Enable use of onboard GPS to determine location	4	2
2	Enable search for location based on street address input	4	2
	Story Points: 2 Total Hours:	8	4

### Story 28: Compare two configurations
Note: This tasks relies on Story 23 to complete
Task ID	Task Description	Estimate	Taken
1	Create UI elements to hold comparison of two or more configurations (desktop)	4
2	Add new tab to results page to allow for comparison (desktop)	1
3	Provide mechanism to select alternate configurations (desktop)	4
4	Create Unit Tests (desktop)	2
5	Create UI elements to hold comparison of two or more configurations (mobile)	4	3
6	Add new tab to results page to allow for comparison (mobile)	1	1
7	Provide mechanism to select alternate configurations (mobile)	4	6
	Story Points: 8 Total Hours:	20	9

### Story 32: Efficiency Checking
Task ID	Task Description	Estimate	Taken
1	Update GAE to include efficiency information in the results class	2
2	Update the summary report in result pane to include information (desktop)	1
3	Update the details table in results pane to include information (desktop)	1
4	Update the summary report in result pane to include information (mobile)	1
5	Update the details table in results pane to include information (mobile)	1
6	Create Unit tests for GAE results.	2
	Story Points: 2 Total Hours:	8	0

### Story 33: Display Panel Output
Task ID	Task Description	Estimate	Taken
1	Update GAE to include panel output information in the results class	2
2	Update the summary report in result pane to include information (desktop)	1
3	Update the details table in results pane to include information (desktop)	1
4	Update the summary report in result pane to include information (mobile)	1
5	Update the details table in results pane to include information (mobile)	1
6	Create Unit tests for GAE results.	2
	Story Points: 2 Total Hours:	8	0