## Sheet1
Iteration 4 Burndown Chart

Story ID	Task ID	Task	Estimate	Assigned	10/10/12	11/10/12	12/10/12	13/10/12	14/10/12	15/10/12	16/10/12	17/10/12	18/10/12	19/10/12	20/10/12	21/10/12	22/10/12	23/10/12	24/10/12
22	1	Enable Swipe navigation of wizard	2	Darran	0
22	2	Create Unit test for Swipe action for navigation	4	Darran	0
22	3	Enable use of onboard GPS to determine location	4	Darran	4	0
22	4	Enable use of onboard gyro's to determine angles for panel setup	4	Darran	4	0
23	1	Create menu to save current configuration/report (desktop)	1	Alex	1	1	0
23	2	Create button to save report to local device	1	Darran/Alex	1	1	1	0
23	3	Create menu to retrieve report from local device	1	Darran/Alex	1	0
23	4	Create functions to store and retrieve solar setup and solar results from local storage (desktop)	2	Alex	2	2	2	0
23	5	Create functions to store and retrieve solar setup and solar results from local storage (mobile)	4	Darran	4	4	0
23	6	Modify UI to handle retrieval of reports and move directly to results pane. (desktop)	2	Alex	2	2	2	2	2	2	2	2	0
23	7	Modify UI to handle retrieval of reports and move directly to results pane. (mobile)	2	Darran	2	2	2	0
23	8	Create Unit tests for storing and retrieving results files.	3	Alex	3	3	3	3	3	3	3	3
24	1	Create menu option for printing, including printer setup	2	Alex	2	2	2	2	2	2	2	2	0
24	2	Create button for printing in results pane in wizard	1	Alex	1	1	1	1	1	1	1	1	0
24	3	Create print output suitable for printing	1	Alex	1	1	1	1	1	1	1	1	0
26	1	Enable use of onboard GPS to determine location	4	Darran	4	0
26	2	Enable search for location based on street address input	4	Darran	4	0
28	1	Create UI elements to hold comparison of two or more configurations (desktop)	4		4	4	4	4	4
28	2	Add new tab to results page to allow for comparison (desktop)	1		1	1	1	1	1
28	3	Provide mechanism to select alternate configurations (desktop)	4		4	4	4	4	4
28	4	Create Unit Tests (desktop)	2		2	2	2	2	2
28	5	Create UI elements to hold comparison of two or more configurations (mobile)	4	Darran	4	4	4	0
28	6	Add new tab to results page to allow for comparison (mobile)	1	Darran	1	1	1	0
28	7	Provide mechanism to select alternate configurations (mobile)	4	Darran	4	4	4	2	0
32	1	Update GAE to include efficiency information in the results class	2		2	2	2	2	2
32	2	Update the summary report in result pane to include information (desktop)	1		1	1	1	1	1
32	3	Update the details table in results pane to include information (desktop)	1		1	1	1	1	1
32	4	Update the summary report in result pane to include information (mobile)	1	Darran	1	1	1	1	1	1	1	1	2	0
32	5	Update the details table in results pane to include information (mobile)	1	Darran	1	1	1	1	1	1	1	1	2	0
32	6	Create Unit tests for GAE results.	2		2	2	2	2	2
33	1	Update GAE to include panel output information in the results class	2		2	2	2	2	2
33	2	Update the summary report in result pane to include information (desktop)	1		1	1	1	1	1
33	3	Update the details table in results pane to include information (desktop)	1		1	1	1	1	1
33	4	Update the summary report in result pane to include information (mobile)	1	Darran	1	1	1	1	1	1	1	1	2	0
33	5	Update the details table in results pane to include information (mobile)	1	Darran	1	1	1	1	1	1	1	1	2	0
33	6	Create Unit tests for GAE results.	2		2	2	2	2	2

		Total Hours Remaining	78		72	55	50	38	36	0	0	0	0	0	0	0	0
		Tasks Completed	36		2	5	2	5	1	0	0	0	0	4	0	4	0	0	0
		Tasks Remaining			34	29	27	22	21	21	21	21	21	21	21	21
		Ideal Burndown			76	70.5714285714	65.1428571429	59.7142857143	54.2857142857	48.8571428571	43.4285714286	38	32.5714285714	27.1428571429	21.7142857143	16.2857142857	10.8571428571	5.4285714286	0
		Day			0	1	2	3	4	5	6	7	8	9	10	11	12	13	14
Burndown Chart
Day
Hours