## Sheet1
Iteration 3 Burndown Chart

Story ID	Task ID	Task	Estimate	Assigned	19/09/12	20/09/12	21/09/12	22/09/12	30/09/12	01/10/12	02/10/12	03/10/12	04/10/12	05/10/12	06/10/12	07/10/12	08/10/12	09/10/12	10/10/12
11	1	Update Solar Panel Class with efficiency loss information.	1		1
11	2	Update Inverter Class with efficiency loss information.	1		1
11	3	Update Unit tests for Solar Panel Class for new information.	1		1
11	4	Update Unit tests for Inverter Class for new information.	1		1
11	5	Update calculation engine in GAE to account for efficiency loss on Solar Panels and Inverters.	2		2
11	6	Update Unit Tests for calculation engine in GAE.	1		1
11	7	Update Results Pane in Desktop to include efficiency loss rows for equipment. (tabulated information pane).	3		3
11	8	Update Unit Tests to ensure this informtion is displayed.	2		2
13	1	Create Tariff Class to hold tariff information.	2		2	2	2
13	2	Create Unit Tests for Class	2		2	2	2
13	3	Create Webservice for Tariff Rate lookup	1		1	1	1
13	4	Create Datastore object to hold tariff information on GAE	1		1	1	1
13	5	Create Unit Tests for Datastore Components	1		1	1	1
13	6	Create Unit Tests for Webservice Components	1		1	1	1
13	7	Create Unit Tests for Webservice Client Components	1		1	1	1
13	8	Create UI elements to select predefined tariffs, including fetching from webservice	2		2	2	2
13	9	Create Unit Tests for UI elements to perform search and field population	1		1	1	1
13	10	Research Tariff rates for each state in Australia, and input into GAE.	6		6	6	5
14	1	Update calculation engine in GAE to output power generation figures into the returned results.	2		2
14	2	Update Unit Tests for calculation engine in GAE	3		3
14	3	Update Results Pane in Desktop to include output power generation row. (tabulated information pane).	3		3
14	4	Update Unit Tests to ensure this informtion is displayed.	2		2
27	1	Determine math formulae for the number of hours per day by month based on location on earth.	2		2
27	2	Update calculation engine in GAE to account for daylight hours in each month.	1		1
27	3	Update Unit Tests for calculation engine in GAE	3		3
22	1	Create Activity Pages based on the Desktop Wizard Workflow. (Skeleton Pages, with working navigation). (Note: Equivalent to Wizard Class in desktop)	10		10
22	2	Create/Implement Solar Setup Description Pane (Note: Equivalent to WizardSetupDescription Class in desktop)	1		1
22	3	Create/Implement User Costs Pane (Note: Equivalent to WizardUserCosts Class in desktop)	1		1
22	4	Create/Implement Setup Electrical Pane (Note: Equivalent to WizardSetupElectrical Class in desktop)	3		3
22	5	Create/Implement Solar Panel Configuration Pane (Note: Equivalent to WizardSolarPanels Class in desktop)	3		3
22	6	Create/Implement Solar Setup Confirmation Pane (Note: Equivalent to WizardSetupConfirmation Class in desktop)	1		1
22	7	Create/Implement Solar Results Pane (Note: Equivalent to WizardResults Class in desktop)	2		2
22	8	Create/Implement Solar Finish Pane (Note: Equivalent to WizardFinish Class in desktop)	1		1
22	9	Create Unit Tests for UI	5		5

		Total Hours Remaining	73		73	0	0	0	0	0	0	0	0	0	0	0	0	0	0
		Tasks Completed			0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
		Tasks Remaining			34	34	34	34	34	34	34	34	34	34	34	34	34	34	34
		Ideal Burndown			73	67.78571429	62.57142857	57.35714286	52.14285714	46.92857143	41.71428571	36.5	31.28571429	26.07142857	20.85714286	15.64285714	10.42857143	5.214285714	0
		Day			0	1	2	3	4	5	6	7	8	9	10	11	12	13	14
Burndown Chart
Hours
Day