## Sheet1
Iteration 2 Burndown Chart

Story ID	Task ID	Task	Estimate	Assigned	05/09/12	06/09/12	07/09/12	08/09/12	09/09/12	10/09/12	11/09/12	12/09/12	13/09/12	14/09/12	15/09/12	16/09/12	17/09/12	18/09/12	19/09/12
2	1	Create Webservice for Solar Panel Information Lookup	1
2	2	Create Datastore object to hold Solar Panel information on GAE	1
2	3	Create Webservice for Inverter Information Lookup	1
2	4	Create Datastore object to hold Inverter information on GAE	1
2	5	Create UI element to allow searching for and retrieving information from the webservice, including population of fields.	2
2	6	Create Unit Tests for Datastore Components	1
2	7	Create Unit Tests for Webservice Components	1
2	8	Create Unit Tests for Webservice Client Components	1
2	9	Create Unit Tests for UI elements to perform search and field population	2
4	1	Create UI element to allow searching for and retrieving information from the webservice, including population of fields.	2
4	2	Create Unit Tests for UI elements to perform search and field population.	2
6	1	Develop mathematical model for efficiency loss on panels	2
6	2	Add algorithm into the SolarPanel Class so can be accessed in client directly, or used by the server for bulk calculations	1
6	3	Create Unit Tests mathematical model	2
6	4	Update UI (In Solar Panel Wizard) to display the loss.	1
6	5	Create Unit Tests for UI updates.	1
8	1	Create UI element to allow searching for and retrieving information from the webservice, including population of fields.	2
8	2	Create Unit Tests for UI elements to perform search and field population.	1
10	1	Create UI element to allow searching for and retrieving information from the webservice, including population of fields.	2
10	2	Create Unit Tests for UI elements to perform search and field population.	1
16	1	Modify Algorithm in webservice to take into account inverter life, and include replacement costs as needed.	2
16	2	Modify Unit Tests for new functionality.	1
17	1	Modify UI elements to be able to handle both Daily and Monthly usage input.	2
17	2	Modify Unit Tests for new functionality.	1
18	1	Modify UI elements to be able to handle both Daily and hourly usage input.	2
18	2	Modify Unit Tests for new functionality.	1
21	1	Modify UI elements to include display of solar panel distribution based on direction.	2
21	2	Modify Unit Tests for new functionality.	1
25	1	Create Location Class to hold location information, including: Location Name/City/State/Country, Latitude, Longitude, Daily Avg Daylight hours (per month), Average Cloud Days (per month)	2	Darran
25	2	Create Unit Tests for Class	1	Darran
25	3	Create Webservice for Location Information Lookup, Modifcation and Addition.	1	Darran
25	4	Create Datastore object to hold Location information on GAE	1	Darran
25	5	Create Unit Tests for Datastore Components	1	Darran
25	6	Create Unit Tests for Webservice Components	1	Darran
25	7	Create Unit Tests for Webservice Client Components	1	Darran
25	8	Create UI elements to display Location Information, including fetching from webservice	2	Darran
25	9	Create Unit Tests for UI elements to perform search and field population	1	Darran
25	10	Update Calculation Algorithm on GAE to allow for locaiton information to enhance calculations	2	Darran
25	11	Modify Unit Test on Calculation Algorithm to take into account location information.	2	Darran
25	12	Create Dialog to manually enter Location Information, and allow saving of information to GAE.	1	Darran
25	13	Create Unit Tests for UI elements to manually input information.	1	Darran
29	3	Display Monthly Savings Data Request to webservice	1	Luke
29	4	Display Monthly Savings Processing on webservice	4	Luke
29	5	Display Monthly Savings Data Return from webservice	3	Luke
29	6	Display Monthly Savings Webservice GUI Dialog boxes	1	Luke
30	1	Modify result information to allow switch between monthly and annual savings.	1
30	2	Update UI elements to allow switching between both monthly and annual savings.	1
30	3	Modify Unit Tests for new functionality.	1
30	4	Create Unit Tests for new UI elements.	1
36	1	Modify Wizard UI to have Sidebar navigator	3	Darran
36	1	Create UI Tests for sidebar	1	Darran

		Total Hours Remaining			0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
		Tasks Completed			0	0	0	0	0	0	0	0
		Tasks Remaining			49	49	49	49	49	49	49	49	49	49	49	49	49	49	49
		Ideal Burndown			59	54.7857142857	50.5714285714	46.3571428571	42.1428571429	37.9285714286	33.7142857143	29.5	25.2857142857	21.0714285714	16.8571428571	12.6428571429	8.4285714286	4.2142857143	0
		Day			0	1	2	3	4	5	6	7	8	9	10	11	12	13	14
Burndown Chart
Iteration 2
Day
Hours