## Sheet1
Story ID	Title	Priority	Points	Hours	Iteration	Assigned To
36	Dekstop Application	M	1	3	1	Darran
1	Hardware cost input	M	1	3	1	Alex
3	System Size input	M	1	3	1	Alex
5	Input Panel Distribution	M	1	3	1	Alex
7	Input Panel Efficiency data	M	1	3	1	Alex
9	Panel lifetime input	M	1	3	1	Michael
12	Tariff rate input	C	1	3	1	Michael
15	Input inverter efficiency	M	1	3	1	Michael
19	Inverter lifetime input	M	1	3	1	Michael
20	Monthly power usage input	M	1	3	1	Alex/Michael
29	Display monthly savings	M	4	13	1	Luke
34	System Infrastructure	M	2	5	1	Darran
35	CI Services	M	2	5	1	Darran

2	Hardware cost fetching	S	4	11	2	Alex/Michael
4	System Size fetching	M	1	4	2	Alex/Michael
6	Efficiency loss calculation	M	2	7	2	Alex/Michael
8	Efficiency loss data fetching	S	1	3	2	Alex/Michael
10	Panel lifetime fetching	S	1	3	2	Alex/Michael
16	Factoring in inverter cost	M	1	3	2	Alex/Michael
17	Daily power usage input	M	1	3	2	Alex/Michael
18	Average daytime hourly power usage	M	1	3	2	Alex/Michael
21	Auto-fill roof area percentages	M	1	3	2	Alex/Michael
25	Location input	S	4	17	2	Darran
30	Display cumulative annual savings	M	1	4	2	Luke
29	Display monthly savings	M	4	13	2	Luke
36	Modify UI to include Sidebar	M	1	2	2	Darran

11	Display estimated efficiency over life	S	4	12	3	Michael
13	Tariff rate fetching	C	4	18	3	Alex
14	Display power generation	S	4	10	3	Luke
27	Average daylight hours for location	S	2	6	3	Luke
22	Mobile application (part A)	M	8	27	3	Darran

22	Mobile application (part B)	M	4	14	4	Darran
23	Saving reports	C	4	14	4
24	Printing reports	C	1	8	4
26	Location fetching	S	2	8	4
32	Efficiency checking	C	2	8	4
33	Display panel output	C	2	8	4

28	Compare two configurations	C	8		5

31	Commercial setup calculations	C	32		6	luke