## Sheet1
Iteration 2 Burndown Chart

Story ID	Task ID	Task	Estimate	Assigned	05/09/12	06/09/12	07/09/12	08/09/12	09/09/12	10/09/12	11/09/12	12/09/12	13/09/12	14/09/12	15/09/12	16/09/12	17/09/12	18/09/12	19/09/12
2	1	Create Webservice for Solar Panel Information Lookup	1	Alex/Michael	1	1
2	2	Create Datastore object to hold Solar Panel information on GAE	1	Alex/Michael	1	1
2	3	Create Webservice for Inverter Information Lookup	1	Alex/Michael	1	1
2	4	Create Datastore object to hold Inverter information on GAE	1	Alex/Michael	1	1
2	5	Create UI element to allow searching for and retrieving information from the webservice, including population of fields.	2	Alex/Michael	2	2
2	6	Create Unit Tests for Datastore Components	1	Alex/Michael	1	1
2	7	Create Unit Tests for Webservice Components	1	Alex/Michael	1	1
2	8	Create Unit Tests for Webservice Client Components	1	Alex/Michael	1	1
2	9	Create Unit Tests for UI elements to perform search and field population	2	Alex/Michael	2	2
4	1	Create UI element to allow searching for and retrieving information from the webservice, including population of fields.	2	Alex/Michael	2	2
4	2	Create Unit Tests for UI elements to perform search and field population.	2	Alex/Michael	2	2
6	1	Develop mathematical model for efficiency loss on panels	2	Alex/Michael	2	2
6	2	Add algorithm into the SolarPanel Class so can be accessed in client directly, or used by the server for bulk calculations	1	Alex/Michael	1	1
6	3	Create Unit Tests mathematical model	2	Alex/Michael	2	2
6	4	Update UI (In Solar Panel Wizard) to display the loss.	1	Alex/Michael	1	1
6	5	Create Unit Tests for UI updates.	1	Alex/Michael	1	1
8	1	Create UI element to allow searching for and retrieving information from the webservice, including population of fields.	2	Alex/Michael	2	2
8	2	Create Unit Tests for UI elements to perform search and field population.	1	Alex/Michael	1	1
10	1	Create UI element to allow searching for and retrieving information from the webservice, including population of fields.	2	Alex/Michael	2	2
10	2	Create Unit Tests for UI elements to perform search and field population.	1	Alex/Michael	1	1
16	1	Modify Algorithm in webservice to take into account inverter life, and include replacement costs as needed.	2	Alex/Michael	2	2
16	2	Modify Unit Tests for new functionality.	1	Alex/Michael	1	1
17	1	Modify UI elements to be able to handle both Daily and Monthly usage input.	2	Alex/Michael	2	2
17	2	Modify Unit Tests for new functionality.	1	Alex/Michael	1	1
18	1	Modify UI elements to be able to handle both Daily and hourly usage input.	2	Alex/Michael	2	2
18	2	Modify Unit Tests for new functionality.	1	Alex/Michael	1	1
21	1	Modify UI elements to include display of solar panel distribution based on direction.	2	Alex/Michael	2	2
21	2	Modify Unit Tests for new functionality.	1	Alex/Michael	1	1
25	1	Create Location Class to hold location information, including: Location Name/City/State/Country, Latitude, Longitude, Daily Avg Daylight hours (per month), Average Cloud Days (per month)	2	Darran	2	0
25	2	Create Unit Tests for Class	1	Darran	1	1
25	3	Create Webservice for Location Information Lookup, Modifcation and Addition.	1	Darran	1	1
25	4	Create Datastore object to hold Location information on GAE	1	Darran	1	1
25	5	Create Unit Tests for Datastore Components	1	Darran	1	1
25	6	Create Unit Tests for Webservice Components	1	Darran	1	1
25	7	Create Unit Tests for Webservice Client Components	1	Darran	1	1
25	8	Create UI elements to display Location Information, including fetching from webservice	2	Darran	2	0
25	9	Create Unit Tests for UI elements to perform search and field population	1	Darran	1	1
25	10	Update Calculation Algorithm on GAE to allow for locaiton information to enhance calculations	2	Darran	2	2
25	11	Modify Unit Test on Calculation Algorithm to take into account location information.	2	Darran	2	2
25	12	Create Dialog to manually enter Location Information, and allow saving of information to GAE.	1	Darran	1	0
25	13	Create Unit Tests for UI elements to manually input information.	1	Darran	1	1
29	3	Display Monthly Savings Data Request to webservice	1	Luke	1	1
29	4	Display Monthly Savings Processing on webservice	4	Luke	4	4
29	5	Display Monthly Savings Data Return from webservice	3	Luke	3	3
29	6	Display Monthly Savings Webservice GUI Dialog boxes	1	Luke	1	1
30	1	Modify result information to allow switch between monthly and annual savings.	1	Alex/Michael	1	1
30	2	Update UI elements to allow switching between both monthly and annual savings.	1	Alex/Michael	1	1
30	3	Modify Unit Tests for new functionality.	1	Alex/Michael	1	1
30	4	Create Unit Tests for new UI elements.	1	Alex/Michael	1	1
36	1	Modify Wizard UI to have Sidebar navigator	3	Darran	3	0
36	1	Create UI Tests for sidebar	1	Darran	1	1

		Total Hours Remaining			74	66	0	0	0	0	0	0	0	0	0	0	0	0	0
		Tasks Completed			0	4	0	0	0	0	0	0	0	0
		Tasks Remaining			49	45	45	45	45	45	45	45	45	45	45	45	45	45	45
		Ideal Burndown			74	68.7142857143	63.4285714286	58.1428571429	52.8571428571	47.5714285714	42.2857142857	37	31.7142857143	26.4285714286	21.1428571429	15.8571428571	10.5714285714	5.2857142857	0
		Day			0	1	2	3	4	5	6	7	8	9	10	11	12	13	14
Burndown Chart
Iteration 2
Day
Hours