## Sheet1
Story ID	Title	Priority	Points	Hours	Iteration	Assigned To
36	Dekstop Application	M	1	3	1	Darran
1	Hardware cost input	M	1	3	1	Alex
3	System Size input	M	1	3	1	Alex
5	Input Panel Distribution	M	1	3	1	Alex
7	Input Panel Efficiency data	M	1	3	1	Alex
9	Panel lifetime input	M	1	3	1	Michael
12	Tariff rate input	C	1	3	1	Michael
15	Input inverter efficiency	M	1	3	1	Michael
19	Inverter lifetime input	M	1	3	1	Michael
20	Monthly power usage input	M	1	3	1	Alex/Michael
29	Display monthly savings	M	4	13	1	Luke
34	System Infrastructure	M	2	5	1	Darran
35	CI Services	M	2	5	1	Darran

2	Hardware cost fetching	S	2		2
4	System Size fetching	M	2		2
6	Efficiency loss calculation	M	2		2
16	Factoring in inverter cost	M	1		2
17	Daily power usage input	M	1		2
18	Average daytime hourly power usage	M	1		2
21	Auto-fill roof area percentages	M	1		2
25	Location input	S	4		2
30	Display cumulative annual savings	M	1		2

8	Efficiency loss data fetching	S	4		3
10	Panel lifetime fetching	S	2		3
11	Display estaimted efficiency over life	S	4		3
13	Tariff rate fetching	C	4		3
14	Display power generation	S	4		3
27	Average daylight hours for location	S	2		3

22	Mobile application	M	16		3,4
26	Location fetching	S	2		4
24	Printing reports	C	1		4

23	Saving reports	C	8		5
28	Compare two configurations	C	8		5
32	Efficiency checking	C	2		5
33	Display panel output	C	2		5

31	Commercial setup calculations	C	32		6	luke