Iteration 2 Plan
Team Anonymous
Student Number	Team Member Name
7538073	Alexander Covlin
8311382	Michael Munchin
7377495	Luke Durkan
7627505	Darran Kartaschew

Tutor: Renford Law
Version: 1.0
Date: 4/9/2012

# Iteration 2 Plan Summary
## Release 1 – iteration 2.
Delivery date: 19-Sep-2012	Total Story Points:23
Current Velocity: 18

Improve user interface
The system will give the user options from the database so they can create a solution based on existing equipment. This will allow a user to select a more realistic solution with current technology limitations in place. The user will still be able to enter their own values if the desire.
Story ID	Story Title	Story Points
2	Hardware cost fetching	4
4	System Size fetching	1
6	Efficiency loss calculation	2
8	Efficiency loss data fetching	1
10	Panel lifetime fetching	1
16	Factoring in inverter cost	1
17	Daily power usage input	1
18	Average daytime hourly power usage	1
21	Auto-fill roof area percentages	1
25	Location input	4
30	Display cumulative annual savings	1
29	Display Monthly Savings*	4
36	Modify UI to include Navigation Sidebar*	1
	Story Point Sub-Total:	23

# Iteration Plan
Total Points:	23	Total Hours: 76
### Story 2: Hardware Cost Fetching
Note: Story 4, 8 and 10 dependent on this story.
Task ID	Task Description	Estimate	Taken
1	Create Webservice for Solar Panel Information Lookup	1 hour	4 hour
2	Create Datastore object to hold Solar Panel information on GAE	1 hour	3 hour
3	Create Webservice for Inverter Information Lookup	1 hour	3 hour
4	Create Datastore object to hold Inverter information on GAE	1 hour	2 hour
5	Create UI element to allow searching for and retrieving information from the webservice, including population of fields.	2 hours	2 hour
6	Create Unit Tests for Datastore Components	1 hour	1 hour
7	Create Unit Tests for Webservice Components	1 hour	1 hour
8	Create Unit Tests for Webservice Client Components	1 hour	1 hour
9	Create Unit Tests for UI elements to perform search and field population	2 hours	2 hour
	Story Points: 4 Total Hours:	11

### Story 4: System Size fetching
Note: Dependent on Story 2 for Webservices.

Task ID	Task Description	Estimate	Taken
1	Create UI element to allow searching for and retrieving information from the webservice, including population of fields.	2 hours	2 hour
2	Create Unit Tests for UI elements to perform search and field population.	2 hours	2 hour
	Story Points: 1 Total Hours:	4

### Story 6: Efficiency loss calculation

Task ID	Task Description	Estimate	Taken
1	Develop mathematical model for efficiency loss on panels.	2 hours	2 hour
2	Add algorithm into the SolarPanel Class so can be accessed in client directly, or used by the server for bulk calculations	1 hour	3 hour
3	Create Unit Tests mathematical model	2 hours	2 hour
4	Update UI (In Solar Panel Wizard) to display the loss.	1 hour	1 hour
5	Create Unit Tests for UI updates.	1 hour
	Story Points: 2 Total Hours:	7

### Story 8: Panel Efficiency Loss fetching
Note: Dependent on Story 2 for Webservices.

Task ID	Task Description	Estimate	Taken
1	Create UI element to allow searching for and retrieving information from the webservice, including population of fields.	2 hours	2 hour
2	Create Unit Tests for UI elements to perform search and field population.	1 hour
	Story Points: 1 Total Hours:	3

### Story 10: Panel lifetime fetching
Note: Dependent on Story 2 for Webservices.

Task ID	Task Description	Estimate	Taken
1	Create UI element to allow searching for and retrieving information from the webservice, including population of fields.	2 hours	2 hour
2	Create Unit Tests for UI elements to perform search and field population.	1 hour
	Story Points: 1 Total Hours:	3

### Story 16: Factoring in inverter cost

Task ID	Task Description	Estimate	Taken
1	Modify Algorithm in webservice to take into account inverter life, and include replacement costs as needed.	2 hours	2 hour
2	Modify Unit Tests for new functionality.	1 hour
	Story Points: 1 Total Hours:	3

### Story 17: Daily power usage input

Task ID	Task Description	Estimate	Taken
1	Modify UI elements to be able to handle both Daily and Monthly usage input.	2 hours	2 hour
2	Modify Unit Tests for new functionality.	1 hour	1 hour
	Story Points: 1 Total Hours:	3

### Story 18: Average daytime hourly power usage
Task ID	Task Description	Estimate	Taken
1	Modify UI elements to be able to handle both Daily and hourly usage input.	2 hours	2 hour
2	Modify Unit Tests for new functionality.	1 hour	1 hour
	Story Points: 1 Total Hours:	3

### Story 21: Auto-fill roof area percentages

Task ID	Task Description	Estimate	Taken
1	Modify UI elements to include display of solar panel distribution based on direction.	2 hours	2 hour
2	Modify Unit Tests for new functionality.	1 hour
	Story Points: 1 Total Hours:	3

### Story 25: Location input

Task ID	Task Description	Estimate	Taken
1	Create Location Class to hold location information, including: Location Name/City/State/Country, Latitude, Longitude, Daily Avg Daylight hours (per month), Average Cloud Days (per month)	2 hour	2
2	Create Unit Tests for Class	1 hour	2
3	Create Webservice for Location Information Lookup, Modifcation and Addition.	1 hour	8
4	Create Datastore object to hold Location information on GAE	1 hour	1
5	Create Unit Tests for Datastore Components	1 hour	1
6	Create Unit Tests for Webservice Components	1 hour	2
7	Create Unit Tests for Webservice Client Components	1 hour	1
8	Create UI elements to display Location Information, including fetching from webservice	2 hour	2
9	Create Unit Tests for UI elements to perform search and field population	1 hour	1
10	Update Calculation Algorithm on GAE to allow for location information to enhance calculations	2 hours
11	Modify Unit Test on Calculation Algorithm to take into account location information.	2 hours
12	Create Dialog to manually enter Location Information, and allow saving of information to GAE.	1 hour	3
13	Create Unit Tests for UI elements to manually input information.	1 hour	1
	Story Points: 4 Total Hours:	17	24

### Story 30: Display cumulative annual savings

Task ID	Task Description	Estimate	Taken
1	Modify result information to allow switch between monthly and annual savings.	1 hour
2	Update UI elements to allow switching between both monthly and annual savings.	1 hour
3	Modify Unit Tests for new functionality.	1 hour
4	Create Unit Tests for new UI elements.	1 hour
	Story Points: 1 Total Hours:	4

### Story 29: Display monthly savings

Task ID	Task Description	Estimate	Taken
1	Create a GUI component to display the data returned	2 hours
2	Create class business layer to hold data	2 hours
3	Create class for data request to webservice	1 hour
4	Create data processing class that takes the input from the webservice, processes it, and completes information in a class to return to client via webservice	6 hours
5	Create class to hold returned data from webservice	1 hour
6	Create webservice progress dialog boxes for UI	1 hour
	Story Points: 4 Total Hours:	13

### Story 36: Desktop Application

Task ID	Task Description	Estimate	Taken
1	Create a GUI component to display the sidebar	1 hour	1
2	Create UI Tests for sidebar operation	2 hours	2
	Story Points: 1 Total Hours:	3	3