## Sheet1
Iteration 4 Burndown Chart

Story ID	Task ID	Task	Estimate	Assigned	10/10/12	11/10/12	12/10/12	13/10/12	14/10/12	15/10/12	16/10/12	17/10/12	18/10/12	19/10/12	20/10/12	21/10/12	22/10/12	23/10/12	24/10/12
22	1	Enable Swipe navigation of wizard	2	Darran	2
22	2	Create Unit test for Swipe action for navigation	4	Darran	4
22	3	Enable use of onboard GPS to determine location	4	Darran	4
22	4	Enable use of onboard gyro's to determine angles for panel setup	4	Darran	4
23	1	Create menu to save current configuration/report (desktop)	1		1
23	2	Create button to save report to local device	1	Darran/?	1
23	3	Create menu to retrieve report from local device	1	Darran/?	1
23	4	Create functions to store and retrieve solar setup and solar results from local storage (desktop)	2		2
23	5	Create functions to store and retrieve solar setup and solar results from local storage (mobile)	4	Darran	4
23	4	Modify UI to handle retrieval of reports and move directly to results pane.	2	Darran/?	2
23	5	Create Unit tests for storing and retrieving results files.	3		3
24	1	Create menu option for printing, including printer setup	2		2
24	2	Create button for printing in results pane in wizard	1		1
24	3	Create print output suitable for printing	1		1
26	1	Enable use of onboard GPS to determine location	4	Darran	4
26	2	Enable search for location based on street address input	4	Darran	4
32	1	Update GAE to include efficiency information in the results class	2		2
32	2	Update the summary report in result pane to include information (desktop)	1		1
32	3	Update the details table in results pane to include information (desktop)	1		1
32	4	Update the summary report in result pane to include information (mobile)	1	Darran	1
32	5	Update the details table in results pane to include information (mobile)	1	Darran	1
32	6	Create Unit tests for GAE results.	2		2
33	1	Update GAE to include panel output information in the results class	2		2
33	2	Update the summary report in result pane to include information (desktop)	1		1
33	3	Update the details table in results pane to include information (desktop)	1		1
33	4	Update the summary report in result pane to include information (mobile)	1	Darran	1
33	5	Update the details table in results pane to include information (mobile)	1	Darran	1
33	6	Create Unit tests for GAE results.	2		2

		Total Hours Remaining	56		56	0	0	0	0	0	0	0	0	0	0	0	0	0	0
		Tasks Completed	28		0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
		Tasks Remaining			28	28	28	28	28	28	28	28	28	28	28	28	28	28	28
		Ideal Burndown			56	52	48	44	40	36	32	28	24	20	16	12	8	4	0
		Day			0	1	2	3	4	5	6	7	8	9	10	11	12	13	14
Burndown Chart
Hours
Day