## Sheet1
Iteration 1 Burndown Chart

Story ID	Task ID	Task	Estimate	Assigned	21/08/12	22/08/12	23/08/12	24/08/12	25/08/12	26/08/12	27/08/12	28/08/12	29/08/12	30/08/12	31/08/12	01/09/12	02/09/12	03/09/12	04/09/12
1	1	GUI Hardware Cost	1	Alex	1
1	2	Hardware Cost in business layer	1	Alex	1
1	3	Hardware Unit Tests	1	Alex	1
3	1	System Size Input GUI	1	Alex	1
3	2	System Size Input Class	1	Alex	1
3	3	System Size Input Unit Test	1	Alex	1
5	1	Panel Distribution GUI	1	Alex	1
5	2	Panel Distribution Class	1	Alex	1
5	3	Panel Distribution Unit Test	1	Alex	1
7	1	Panel Efficiency GUI	1	Alex	1
7	2	Panel Efficiency Class	1	Alex	1
7	3	Panel Efficiency Unit Test	1	Alex	1
9	1	Panel Lifetime GUI	1	Michael	1
9	2	Panel Lifetime Class	1	Michael	1
9	3	Panel Lifetime Unit Test	1	Michael	1
12	1	Tariff GUI	1	Michael	1
12	2	Tariff Class	1	Michael	1
12	3	Tariff Unit Test	1	Michael	1
15	1	Inverter GUI	1	Michael	1
15	2	Inverter Class	1	Michael	1
15	3	Inverter Unit Test	1	Michael	1
19	1	Inverter Lifetime GUI	1	Michael	1
19	2	Inverter Lifetime Class	1	Michael	1
19	3	Inverter Lifetime Unit Test	1	Michael	1
20	1	Monthly Power Usage GUI	1	Alex/Michael	1
20	2	Monthly Power Usage Class	1	Alex/Michael	1
20	3	Monthly Power Usage Unit Test	1	Alex/Michael	1
29	1	Display Monthly Savings GUI	2	Luke	2
29	2	Display Monthly Savings Class	2	Luke	2
29	3	Display Monthly Savings Data Request to webservice	1	Luke	1
29	4	Display Monthly Savings Processing on webservice	6	Luke	6
29	5	Display Monthly Savings Data Return from webservice	1	Luke	1
29	6	Display Monthly Savings Webservice GUI Dialog boxes	1	Luke	1
34	1	Google Account Setup + GAE Setup	1	Darran	1	0
34	2	Create GitHub account + repositories	1	Darran	1	0
34	3	Create basic GAE application and upload to GH+GAE	3	Darran	3	0
35	1	Create Virtual appliance to host Hudson	4	Darran	3	0
35	2	Install and configure Hudson for access	1	Darran	1	1	0
36	1	Create Desktop Application Container	3	Darran	3	1	0

		Total Hours Remaining			52	2	0	0	0	0	0	0	0	0	0	0	0	0	0
		Tasks Completed			0	4	2	0	0	0	0	0	0	0	0	0	0	0	0
		Tasks Remaining			39	35	33	33	33	33	33	33	33	33	33	33	33	33	33
		Ideal Burndown