## Sheet1
Iteration 4 Burndown Chart

Story ID	Task ID	Task	Estimate	Assigned	10/10/12	11/10/12	12/10/12	13/10/12	14/10/12	15/10/12	16/10/12	17/10/12	18/10/12	19/10/12	20/10/12	21/10/12	22/10/12	23/10/12	24/10/12
22	1	Enable Swipe navigation of wizard	2	Darran	0
22	2	Create Unit test for Swipe action for navigation	4	Darran	0
22	3	Enable use of onboard GPS to determine location	4	Darran	4	0
22	4	Enable use of onboard gyro's to determine angles for panel setup	4	Darran	4	0
23	1	Create menu to save current configuration/report (desktop)	1	Alex	1	1	0
23	2	Create button to save report to local device	1	Darran/Alex	1	1	1	0
23	3	Create menu to retrieve report from local device	1	Darran/Alex	1	0
23	4	Create functions to store and retrieve solar setup and solar results from local storage (desktop)	2	Alex	2	2	2	0
23	5	Create functions to store and retrieve solar setup and solar results from local storage (mobile)	4	Darran	4	4	0
23	6	Modify UI to handle retrieval of reports and move directly to results pane. (desktop)	2	Alex	2	2	2	2	2	2	2	2	2	0
23	7	Modify UI to handle retrieval of reports and move directly to results pane. (mobile)	2	Darran	2	2	2	0
23	8	Create Unit tests for storing and retrieving results files.	3	Alex	3	3	3	3	3	3	3	3	3	3
24	1	Create menu option for printing, including printer setup	2	Alex	2	2	2	2	2	2	2	2	2	0
24	2	Create button for printing in results pane in wizard	1	Alex	1	1	1	1	1	1	1	1	1	0
24	3	Create print output suitable for printing	1	Alex	1	1	1	1	1	1	1	1	1	0
26	1	Enable use of onboard GPS to determine location	4	Darran	4	0
26	2	Enable search for location based on street address input	4	Darran	4	0
28	1	Create UI elements to hold comparison of two or more configurations (desktop)	4		4	4	4	4	4
28	2	Add new tab to results page to allow for comparison (desktop)	1		1	1	1	1	1
28	3	Provide mechanism to select alternate configurations (desktop)	4		4	4	4	4	4
28	4	Create Unit Tests (desktop)	2		2	2	2	2	2
28	5	Create UI elements to hold comparison of two or more configurations (mobile)	4	Darran	4	4	4	0
28	6	Add new tab to results page to allow for comparison (mobile)	1	Darran	1	1	1	0
28	7	Provide mechanism to select alternate configurations (mobile)	4	Darran	4	4	4	2	0
32	1	Update GAE to include efficiency information in the results class	2		2	2	2	2	2
32	2	Update the summary report in result pane to include information (desktop)	1		1	1	1	1	1
32	3	Update the details table in results pane to include information (desktop)	1		1	1	1	1	1
32	4	Update the summary report in result pane to include information (mobile)	1	Darran	1	1	1	1	1
32	5	Update the details table in results pane to include information (mobile)	1	Darran	1	1	1	1	1
32	6	Create Unit tests for GAE results.	2		2	2	2	2	2
33	1	Update GAE to include panel output information in the results class	2		2	2	2	2	2
33	2	Update the summary report in result pane to include information (desktop)	1		1	1	1	1	1
33	3	Update the details table in results pane to include information (desktop)	1		1	1	1	1	1
33	4	Update the summary report in result pane to include information (mobile)	1	Darran	1	1	1	1	1
33	5	Update the details table in results pane to include information (mobile)	1	Darran	1	1	1	1	1
33	6	Create Unit tests for GAE results.	2		2	2	2	2	2

		Total Hours Remaining	78		72	55	50	38	36	0	0	0	0	0	0	0	0	0	0
		Tasks Completed	36		2	5	2	5	1	0	0	0	0	0	0	0	0	0	0
		Tasks Remaining			34	29	27	22	21	21	21	21	21	21	21	21	21	21	21
		Ideal Burndown			76	70.57142857	65.14285714	59.71428571	54.28571429	48.85714286	43.42857143	38	32.57142857	27.14285714	21.71428571	16.28571429	10.85714286	5.428571429	0
		Day			0	1	2	3	4	5	6	7	8	9	10	11	12	13	14
Burndown Chart
Hours
Day