## Sheet1
Iteration 2 Burndown Chart

Story ID	Task ID	Task	Estimate	Assigned	05/09/12	06/09/12	07/09/12	08/09/12	09/09/12	10/09/12	11/09/12	12/09/12	13/09/12	14/09/12	15/09/12	16/09/12	17/09/12	18/09/12	19/09/12
2	1	Create Webservice for Solar Panel Information Lookup	1	Alex/Michael	1	1	1	1	1	1	3	0
2	2	Create Datastore object to hold Solar Panel information on GAE	1	Alex/Michael	1	1	1	1	1	1	3	0
2	3	Create Webservice for Inverter Information Lookup	1	Alex/Michael	1	1	1	1	1	1	2	0
2	4	Create Datastore object to hold Inverter information on GAE	1	Alex/Michael	1	1	1	1	1	1	2	0
2	5	Create UI element to allow searching for and retrieving information from the webservice, including population of fields.	2	Alex/Michael	2	2	2	2	2	2	2	2	0
2	6	Create Unit Tests for Datastore Components	1	Alex/Michael	1	1	1	1	1	1	1	1	0
2	7	Create Unit Tests for Webservice Components	1	Alex/Michael	1	1	1	1	1	1	1	1	0
2	8	Create Unit Tests for Webservice Client Components	1	Alex/Michael	1	1	1	1	1	1	1	1	0
2	9	Create Unit Tests for UI elements to perform search and field population	2	Alex/Michael	2	2	2	2	2	2	2	2	1	1	0
4	1	Create UI element to allow searching for and retrieving information from the webservice, including population of fields.	2	Alex/Michael	2	2	2	2	2	2	2	2	0
4	2	Create Unit Tests for UI elements to perform search and field population.	2	Alex/Michael	2	2	2	2	2	2	2	2	0
6	1	Develop mathematical model for efficiency loss on panels	2	Alex/Michael	2	2	2	2	2	2	2	2	0
6	2	Add algorithm into the SolarPanel Class so can be accessed in client directly, or used by the server for bulk calculations	1	Alex/Michael	1	1	1	1	1	1	1	1	0
6	3	Create Unit Tests mathematical model	2	Alex/Michael	2	2	2	2	2	2	2	2	0
6	4	Update UI (In Solar Panel Wizard) to display the loss.	1	Alex/Michael	1	1	1	1	1	1	1	1	0
6	5	Create Unit Tests for UI updates.	1	Alex/Michael	1	1	1	1	1	1	1	1	0
8	1	Create UI element to allow searching for and retrieving information from the webservice, including population of fields.	2	Alex/Michael	2	2	2	2	2	2	2	2	0
8	2	Create Unit Tests for UI elements to perform search and field population.	1	Alex/Michael	1	1	1	1	1	1	1	1	0
10	1	Create UI element to allow searching for and retrieving information from the webservice, including population of fields.	2	Alex/Michael	2	2	2	2	2	2	2	2	0
10	2	Create Unit Tests for UI elements to perform search and field population.	1	Alex/Michael	1	1	1	1	1	1	1	1	0
16	1	Modify Algorithm in webservice to take into account inverter life, and include replacement costs as needed.	2	Alex/Michael	2	2	2	2	2	2	2	2	0
16	2	Modify Unit Tests for new functionality.	1	Alex/Michael	1	1	1	1	1	1	1	1	0
17	1	Modify UI elements to be able to handle both Daily and Monthly usage input.	2	Alex/Michael	2	2	2	2	2	2	2	2	0
17	2	Modify Unit Tests for new functionality.	1	Alex/Michael	1	1	1	1	1	1	1	1	0
18	1	Modify UI elements to be able to handle both Daily and hourly usage input.	2	Alex/Michael	2	2	2	2	2	2	2	2	0
18	2	Modify Unit Tests for new functionality.	1	Alex/Michael	1	1	1	1	1	1	1	1	0
21	1	Modify UI elements to include display of solar panel distribution based on direction.	2	Alex/Michael	2	2	2	2	2	2	2	2	0
21	2	Modify Unit Tests for new functionality.	1	Alex/Michael	1	1	1	1	1	1	1	1	0
25	1	Create Location Class to hold location information, including: Location Name/City/State/Country, Latitude, Longitude, Daily Avg Daylight hours (per month), Average Cloud Days (per month)	2	Darran	2	0
25	2	Create Unit Tests for Class	1	Darran	1	1	1	1	1	1	1	0
25	3	Create Webservice for Location Information Lookup, Modifcation and Addition.	1	Darran	1	1	1	8	0
25	4	Create Datastore object to hold Location information on GAE	1	Darran	1	1	1	3	0
25	5	Create Unit Tests for Datastore Components	1	Darran	1	1	1	1	1	1	1	1	0
25	6	Create Unit Tests for Webservice Components	1	Darran	1	1	1	1	1	1	1	1	0
25	7	Create Unit Tests for Webservice Client Components	1	Darran	1	1	1	1	1	1	1	1	0
25	8	Create UI elements to display Location Information, including fetching from webservice	2	Darran	2	0
25	9	Create Unit Tests for UI elements to perform search and field population	1	Darran	1	1	1	1	1	1	1	1	0
25	10	Update Calculation Algorithm on GAE to allow for locaiton information to enhance calculations	2	Luke	2	2	2	2	2	2	2	2	0
25	11	Modify Unit Test on Calculation Algorithm to take into account location information.	2	Luke	2	2	2	2	2	2	2	2
25	12	Create Dialog to manually enter Location Information, and allow saving of information to GAE.	1	Darran	1	0
25	13	Create Unit Tests for UI elements to manually input information.	1	Darran	1	1	1	1	1	1	1	1	0
29	3	Display Monthly Savings Data Request to webservice	1	Luke	1	1	1	1	1	1	1	1	1	0
29	4	Display Monthly Savings Processing on webservice	4	Luke	4	4	4	4	2	2	2	2	2	2	2	2	2	0
29	5	Display Monthly Savings Data Return from webservice	3	Luke	3	3	3	3	3	2	2	2	2	2	2	2	2	0
29	6	Display Monthly Savings Webservice GUI Dialog boxes	1	Luke	1	1	1	1	1	1	1	1	1	0
30	1	Modify result information to allow switch between monthly and annual savings.	1	Luke	1	1	1	1	1	1	1	1
30	2	Update UI elements to allow switching between both monthly and annual savings.	1	Luke	1	1	1	1	1	1	1	1
30	3	Modify Unit Tests for new functionality.	1	Luke	1	1	1	1	1	1	1	1
30	4	Create Unit Tests for new UI elements.	1	Luke	1	1	1	1	1	1	1	1
36	1	Modify Wizard UI to have Sidebar navigator	3	Darran	3	0
36	1	Create UI Tests for sidebar	1	Darran	1	1	1	1	1	1	1	1	0

		Total Hours Remaining			74	66	66	75	62	61	67	56	52	45	21	18	13	4	4
		Tasks Completed			0	4	0	0	2	0	0	5	3	5	17	3	2	6	0
		Tasks Remaining			51	47	47	47	45	45	45	40	37	32	15	12	10	4	4
		Ideal Burndown			74	68.7142857143	63.4285714286	58.1428571429	52.8571428571	47.5714285714	42.2857142857	37	31.7142857143	26.4285714286	21.1428571429	15.8571428571	10.5714285714	5.2857142857	0
		Day			0	1	2	3	4	5	6	7	8	9	10	11	12	13	14
Burndown Chart
Day
Hours