## Sheet1
Iteration 3 Burndown Chart

Story ID	Task ID	Task	Estimate	Assigned	19/09/12	20/09/12	21/09/12	22/09/12	30/09/12	01/10/12	02/10/12	03/10/12	04/10/12	05/10/12	06/10/12	07/10/12	08/10/12	09/10/12	10/10/12
11	1	Update Solar Panel Class with efficiency loss information.	1		1
11	2	Update Inverter Class with efficiency loss information.	1		1
11	3	Update Unit tests for Solar Panel Class for new information.	1		1
11	4	Update Unit tests for Inverter Class for new information.	1		1
11	5	Update calculation engine in GAE to account for efficiency loss on Solar Panels and Inverters.	2		2
11	6	Update Unit Tests for calculation engine in GAE.	1		1
11	7	Update Results Pane in Desktop to include efficiency loss rows for equipment. (tabulated information pane).	3		3
11	8	Update Unit Tests to ensure this informtion is displayed.	2		2
13	1	Create Tariff Class to hold tariff information.	2		2	2	2
13	2	Create Unit Tests for Class	2		2	2	2
13	3	Create Webservice for Tariff Rate lookup	1		1	1	1
13	4	Create Datastore object to hold tariff information on GAE	1		1	1	1
13	5	Create Unit Tests for Datastore Components	1		1	1	1
13	6	Create Unit Tests for Webservice Components	1		1	1	1
13	7	Create Unit Tests for Webservice Client Components	1		1	1	1
13	8	Create UI elements to select predefined tariffs, including fetching from webservice	2		2	2	2
13	9	Create Unit Tests for UI elements to perform search and field population	1		1	1	1
13	10	Research Tariff rates for each state in Australia, and input into GAE.	6		6	6	5
14	1	Update calculation engine in GAE to output power generation figures into the returned results.	2		2
14	2	Update Unit Tests for calculation engine in GAE	3		3
14	3	Update Results Pane in Desktop to include output power generation row. (tabulated information pane).	3		3
14	4	Update Unit Tests to ensure this informtion is displayed.	2		2
27	1	Determine math formulae for the number of hours per day by month based on location on earth.	2		2
27	2	Update calculation engine in GAE to account for daylight hours in each month.	1		1
27	3	Update Unit Tests for calculation engine in GAE	3		3
22	1	Create Activity Pages based on the Desktop Wizard Workflow. (Skeleton Pages, with working navigation). (Note: Equivalent to Wizard Class in desktop)	10	Darran	10	10	10	10	0
22	2	Create/Implement Solar Setup Description Pane (Note: Equivalent to WizardSetupDescription Class in desktop)	1	Darran	1	1	1	1
22	3	Create/Implement User Costs Pane (Note: Equivalent to WizardUserCosts Class in desktop)	1	Darran	1	1	1	1
22	4	Create/Implement Setup Electrical Pane (Note: Equivalent to WizardSetupElectrical Class in desktop)	3	Darran	3	3	3	3
22	5	Create/Implement Solar Panel Configuration Pane (Note: Equivalent to WizardSolarPanels Class in desktop)	3	Darran	3	3	3	3
22	6	Create/Implement Solar Setup Confirmation Pane (Note: Equivalent to WizardSetupConfirmation Class in desktop)	1	Darran	1	1	1	1
22	7	Create/Implement Solar Results Pane (Note: Equivalent to WizardResults Class in desktop)	2	Darran	2	2	2	2
22	8	Create/Implement Solar Finish Pane (Note: Equivalent to WizardFinish Class in desktop)	1	Darran	1	1	1	1
22	9	Create Unit Tests for UI	5	Darran	5	5	5	5

		Total Hours Remaining	73		73	0	0	0	0	0	0	0	0
		Tasks Completed			0	0	0	0	0	0	0	0
		Tasks Remaining			34	34	34	34	34	34	34	34
		Ideal Burndown			73	67.7857142857	62.5714285714	57.3571428571	52.1428571429	46.9285714286	41.7142857143	36.5	31.2857142857	26.0714285714	20.8571428571	15.6428571429	10.4285714286	5.2142857143	0
		Day			0	1	2	3	4	5	6	7	8	9	10	11	12	13	14
Burndown Chart
Day
Hours