## Sheet1
Iteration 1 Burndown Chart

Story ID	Task ID	Task	Estimate	Assigned	21/08/12	22/08/12	23/08/12	24/08/12	25/08/12	26/08/12	27/08/12	28/08/12	29/08/12	30/08/12	31/08/12	01/09/12	02/09/12	03/09/12	04/09/12
1	1	GUI Hardware Cost	1	Alex	1	1	1	0
1	2	Hardware Cost in business layer	1	Alex	1	1	1	0
1	3	Hardware Unit Tests	1	Alex	1	1	1	1	1	1	1	1
3	1	System KW Size Input GUI	1	Alex	1	1	1	0
3	2	System KW Size Input Class	1	Alex	1	1	1	0
3	3	System KW Size Input Unit Test	1	Alex	1	1	1	1	1	1	1	1
5	1	Panel Distribution GUI	1	Alex	1	1	1	0	1	1	1	1	0
5	2	Panel Distribution Class	1	Alex	1	1	1	0
5	3	Panel Distribution Unit Test	1	Alex	1	1	1	1	1	1	1	1
7	1	Panel Efficiency GUI	1	Alex	1	1	1	0
7	2	Panel Efficiency Class	1	Alex	1	1	1	0
7	3	Panel Efficiency Unit Test	1	Alex	1	1	1	1	1	1	1	1
9	1	Panel Lifetime GUI	1	Alex	1	1	1	0
9	2	Panel Lifetime Class	1	Alex	1	1	1	0
9	3	Panel Lifetime Unit Test	1	Alex	1	1	1	1	1	1	1	1
12	1	Tariff GUI	1	Michael	1	1	1	1	1	1	1	1	0
12	2	Tariff Class	1	Michael	1	1	1	1	1	1	1	1	0
12	3	Tariff Unit Test	1	Michael	1	1	1	1	0
15	1	Inverter GUI	1	Michael	1	1	1	1	1	1	1	1	0
15	2	Inverter Class	1	Michael	1	1	1	1	1	1	1	1	0
15	3	Inverter Unit Test	1	Michael	1	1	1	1	0
19	1	Inverter Lifetime GUI	1	Michael	1	1	1	1	1	1	1	1	0
19	2	Inverter Lifetime Class	1	Michael	1	1	1	1	1	1	1	1	0
19	3	Inverter Lifetime Unit Test	1	Michael	1	1	0
20	1	Monthly Power Usage GUI	1	Michael	1	1	1	1	1	1	1	1	0
20	2	Monthly Power Usage Class	1	Michael	1	1	1	1	1	1	1	1	0
20	3	Monthly Power Usage Unit Test	1	Michael	1	1	0
29	1	Display Monthly Savings GUI	2	Luke	2	0	0	0	0	0	0	0	0
29	2	Display Monthly Savings Class	2	Luke	2	2	0	0	0	0	0	0	0	0
29	3	Display Monthly Savings Data Request to webservice	1	Luke	5	1	5	5	5	5	3	3	3	0	1	1	1	1	1
29	4	Display Monthly Savings Processing on webservice	6	Luke	6	14	14	14	14	11	10	10	10	10	6	6	6	4	4
29	5	Display Monthly Savings Data Return from webservice	1	Luke	5	5	5	5	5	5	3	3	3	3	3	3	3	3
29	6	Display Monthly Savings Webservice GUI Dialog boxes	1	Luke	1	1	1	1	1	1	1	1
34	1	Google Account Setup + GAE Setup	1	Darran	1	0
34	2	Create GitHub account + repositories	1	Darran	1	0
34	3	Create basic GAE application and upload to GH+GAE	3	Darran	3	0
35	1	Create Virtual appliance to host Hudson	4	Darran	3	0
35	2	Install and configure Hudson for access	1	Darran	1	1	0
36	1	Create Desktop Application Container	3	Darran	3	1	0					8	8	0

		Total Hours Remaining			52	42	40	30	31	31	31	31	34	34	24	24	24	24	24
		Tasks Completed			0	4	2	10	0	0	0	0	5	0	2	0	0	0	0
		Tasks Remaining			40	36	34	24	24	24	24	24	19	19	17	17	17	17	17
		Ideal Burndown			52	48.2857142857	44.5714285714	40.8571428571	37.1428571429	33.4285714286	29.7142857143	26	22.2857142857	18.5714285714	14.8571428571	11.1428571429	7.4285714286	3.7142857143	0
		Day			0	1	2	3	4	5	6	7	8	9	10	11	12	13	14
Burndown Chart
Day
Hours