Iteration 3 Plan
Team Anonymous
Student Number	Team Member Name
7538073	Alexander Covlin
8311382	Michael Munchin
7377495	Luke Durkan
7627505	Darran Kartaschew

Tutor: Renford Law
Version: 1.0
Date: 18/9/2012

# Iteration 3 Plan Summary
## Release 2 – iteration 1.
Delivery date: 10-Oct-2012	Total Story Points:22
Current Velocity: 20

Model Refinement and Mobile Application
The system will be able to give a more accurate cost analysis of the system by taking into account environmental factors and location information. It will allow the user to not only see the lifetime of the panel but the estimated efficiency of the panel over its lifetime as well as being able to see the Tariff rates from different suppliers in their area.
The initial version of the Mobile Application will be developed, and be equivalent in functionality to that as delivered by the desktop application in Release 1.
Story ID	Story Title	Story Points
11	Display estimated efficiency over life	4
13	Tariff Rate Fetching	4
14	Display Power Generation	4
27	Average daylight hours for location	2
22	Mobile Application (part A)	8
	Story Point Sub-Total:	22

# Iteration Plan
Total Points:	22	Total Hours: 75
### Story 11: Display estimated efficiency over life

Task ID	Task Description	Estimate	Taken
1	Update Solar Panel Class with efficiency loss information.	1 hour
2	Update Inverter Class with efficiency loss information.	1 hour
3	Update Unit tests for Solar Panel Class for new information.	1 hour
4	Update Unit tests for Inverter Class for new information.	1 hour
5	Update calculation engine in GAE to account for efficiency loss on Solar Panels and Inverters.	2 hours
6	Update Unit Tests for calculation engine in GAE.	1 hour
7	Update Results Pane in Desktop to include efficiency loss rows for equipment. (tabulated information pane).	3 hours
8	Update Unit Tests to ensure this information is displayed.	2 hours
	Story Points: 4 Total Hours:	12

### Story 13: Tariff Rate Fetching

Task ID	Task Description	Estimate	Taken
1	Create Tariff Class to hold tariff information.	2 hours	2h
2	Create Unit Tests for Class	2 hours	2h
3	Create Webservice for Tariff Rate lookup	1 hour	4h
4	Create Datastore object to hold tariff information on GAE	1 hour	1h
5	Create Unit Tests for Datastore Components	1 hour	1h
6	Create Unit Tests for Webservice Components	1 hour	1h
7	Create Unit Tests for Webservice Client Components	1 hour	1h
8	Create UI elements to select predefined tariffs, including fetching from webservice	2 hour
9	Create Unit Tests for UI elements to perform search and field population	1 hour	1h
10	Research Tariff rates for each state in Australia, and input into GAE.	6 hours	7h
	Story Points: 4 Total Hours:	18

### Story 14: Display Power Generation

Task ID	Task Description	Estimate	Taken
1	Update calculation engine in GAE to output power generation figures into the returned results.	2 hours
2	Update Unit Tests for calculation engine in GAE	3 hours
3	Update Results Pane in Desktop to include output power generation row. (tabulated information pane).	3 hours
4	Update Unit Tests to ensure this information is displayed.	2 hours
	Story Points: 4 Total Hours:	10

### Story 27: Average daylight hours for location

Task ID	Task Description	Estimate	Taken
1	Determine math formulae for the number of hours per day by month based on location on earth.	2 hours
2	Update calculation engine in GAE to account for daylight hours in each month.	1 hour
3	Update Unit Tests for calculation engine in GAE	3 hours
	Story Points: 2 Total Hours:	6

### Story 22: Mobile Application (part A)
Note: The aim of Part A is to simple replicate the Desktop Application of Release 1 on Android Tablet. No implementation of features to take advantage of underlying hardware is to take place.
Task ID	Task Description	Estimate	Taken
1	Create Activity Pages based on the Desktop Wizard Workflow. (Skeleton Pages, with working navigation). (Note: Equivalent to Wizard Class in desktop)	10 hours	12
2	Create/Implement Solar Setup Description Pane (Note: Equivalent to WizardSetupDescription Class in desktop)	1 hour	6
3	Create/Implement User Costs Pane (Note: Equivalent to WizardUserCosts Class in desktop)	1 hour	4
4	Create/Implement Setup Electrical Pane (Note: Equivalent to WizardSetupElectrical Class in desktop)	3 hours	6
5	Create/Implement Solar Panel Configuration Pane (Note: Equivalent to WizardSolarPanels Class in desktop)	3 hours	10
6	Create/Implement Solar Setup Confirmation Pane (Note: Equivalent to WizardSetupConfirmation Class in desktop)	1 hour	1
7	Create/Implement Solar Results Pane (Note: Equivalent to WizardResults Class in desktop)	2 hours	9
8	Create/Implement Solar Finish Pane (Note: Equivalent to WizardFinish Class in desktop)	1 hour	1
9	Create Unit Tests for UI	5 hours
	Story Points: 8 Total Hours:	27	49